## GanttChart
| SIMPLIX PROJECT | [14 empty] | Gantt Chart Template © 2016 by Vertex42.com.
CHEF DE PROJECT ADEL BOUACHRAOUI
| Start: | 2025-10-22 | [9 empty] | Display: | Weekly | time axis 2025-10-20 to 2026-11-16
| End: | 2026-04-01 | [9 empty] | Week: | 1 |  |  | 2025-10-20: Weeks 1-7; 2025-12-08: Weeks 8-14; 2026-01-26: Weeks 15-21; 2026-03-16: Weeks 22-28; 2026-05-04: Weeks 29-35; 2026-06-22: Weeks 36-42; 2026-08-10: Weeks 43-49; 2026-09-28: Weeks 50-56
|  | Unhide columns to edit tasks ► | [9 empty] | ◄ |  |  |  | 2025-10-20: Oct YYYY - Dec YYYY; 2025-12-08: Dec YYYY - Jan YYYY; 2026-01-26: Jan YYYY - Mar YYYY; 2026-03-16: Mar YYYY - Apr YYYY; 2026-05-04: May YYYY - Jun YYYY; 2026-06-22: Jun YYYY - Aug YYYY; 2026-08-10: Aug YYYY - Sep YYYY; 2026-09-28: Sep YYYY - Nov YYYY
WBS Level | WBS | Task | Lead | Budget | Prede cessor | Start | End | Work Days | Cal. Days | % Done | Color | Start | End | Work Days | Cal. Days
[16 empty] | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9
1 | 1 | Création de la VM Débian |  |  |  | 2025-10-22 | 2026-01-28 | 3 |  |  | g | 2025-10-22 | 2026-01-28 | 3 | 99 | bar: 24; 2
2 | 1.1 | Récupération Documentation |  |  |  | 2025-10-22 | 2025-11-12 | 2 |  |  | 3 | 2025-10-22 | 2025-11-12 | 2 | 22
2 | 1.2 | Configuration VM |  |  |  | 2025-11-12 | 2025-11-12 | 1 |  |  | 3 | 2025-11-12 | 2025-11-12 | 1 | 1
2 | 1.3 | Documentation NGINX |  |  |  | 2025-11-12 | 2025-11-12 | 1 |  |  | 3 | 2025-11-12 | 2025-11-12 | 1 | 1
2 | 1.4 | Installation NGINX + CONFIGURATION |  |  |  | 2025-11-12 | 2025-12-11 | 1 |  |  | 3 | 2025-11-12 | 2025-12-11 | 1 | 30
2 | 1.5 | Création de l'Image Docker de la VM |  |  |  | 2025-12-11 | 2026-01-07 | 5 |  |  | 3 | 2025-12-11 | 2026-01-07 | 5 | 28
2 | 1.6 | Récupération + Implémentation de la Solution Web |  |  |  | 2026-01-07 | 2026-01-07 | 1 |  |  | 3 | 2026-01-07 | 2026-01-07 | 1 | 1
2 | 1.7 | Déploiement de la Solution |  |  |  | 2026-01-08 | 2026-01-28 | 2 |  |  | 3 | 2026-01-08 | 2026-01-28 | 2 | 21 | bar: 2
1 | 2 | Dévellopement de la Solution Web |  |  |  | 2025-10-22 | 2026-01-28 |  |  |  | g | 2025-10-22 | 2026-01-28 | 67 | 99 | bar: 2
2 | 2.1 | Création + Configuration Base de Donnée |  |  |  | 2025-10-22 | 2025-12-11 | 4 |  |  | 1 | 2025-10-22 | 2025-12-11 | 4 | 51
2 | 2.2 | Dévellopement Front |  |  |  | 2025-10-22 | 2026-01-07 | 5 |  |  | 3 | 2025-10-22 | 2026-01-07 | 5 | 78
2 | 2.3 | Dévellopement Back-End |  |  |  | 2025-10-22 | 2026-01-28 | 6 |  |  | 3 | 2025-10-22 | 2026-01-28 | 6 | 99 | bar: 2
1 | 3 | Ensembles des Supports Gestion d'Equipe |  |  |  | 2025-10-22 | 2026-04-01 |  |  |  | g | 2025-10-22 | 2026-04-01 | 112 | 162 | bar: 6
2 | 3.1 | Diagramme de Gantt |  |  |  | 2025-10-22 | 2025-10-22 | 1 |  |  | 1 | 2025-10-22 | 2025-10-22 | 1 | 1
2 | 3.2 | RACI |  |  |  | 2025-10-22 | 2025-10-22 | 1 |  |  | 1 | 2025-10-22 | 2025-10-22 | 1 | 1
2 | 3.3 | Analyse des Risques |  |  |  | 2025-10-22 | 2025-10-22 | 1 |  |  | 1 | 2025-10-22 | 2025-10-22 | 1 | 1
2 | 3.4 | Power Point V1 |  |  |  | 2025-10-22 | 2025-12-11 | 3 |  |  | 1 | 2025-10-22 | 2025-12-11 | 3 | 51
2 | 3.5 | Power Point V2 |  |  |  | 2026-03-11 | 2026-04-01 | 2 |  |  | 1 | 2026-03-11 | 2026-04-01 | 2 | 22 | bar: 6
2 | 3.6 | Préparation de L'Oral Final |  |  |  | 2026-03-11 | 2026-04-01 | 1 |  |  | 1 | 2026-03-11 | 2026-04-01 | 1 | 22 | bar: 6
1 | 4 | Recherche De Client |  |  |  | 2025-10-22 | 2026-04-01 |  |  |  | g | 2025-10-22 | 2026-04-01 | 112 | 162 | bar: 6
2 | 4.1 | Préparation Plan Marckéting |  |  |  | 2026-01-28 | 2026-03-11 | 2 |  |  | 1 | 2026-01-28 | 2026-03-11 | 2 | 43
2 | 4.2 | Analyse du Marché |  |  |  | 2026-01-28 | 2026-03-11 | 2 |  |  | 1 | 2026-01-28 | 2026-03-11 | 2 | 43
2 | 4.3 | Liste de Clients Potentiel |  |  |  | 2026-01-28 | 2026-03-11 | 2 |  |  | 1 | 2026-01-28 | 2026-03-11 | 2 | 43
2 | 4.4 | Démarchage de Clientèle |  |  |  | 2026-03-11 | 2026-04-01 | 2 |  |  | 1 | 2026-03-11 | 2026-04-01 | 2 | 22 | bar: 6
1 | 5 | Dévellopement de la Solution Web |  |  |  | 2025-10-22 | 2026-01-28 |  |  |  | g | 2025-10-22 | 2026-01-28 | 67 | 99 | bar: 2
2 | 5.1 | Création + Configuration Base de Donnée |  |  |  | 2025-10-22 | 2025-12-11 | 3 |  |  | 1 | 2025-10-22 | 2025-12-11 | 3 | 51
2 | 5.2 | Dévellopement Front |  |  |  | 2025-10-22 | 2026-01-07 | 4 |  |  | 3 | 2025-10-22 | 2026-01-07 | 4 | 78
2 | 5.3 | Dévellopement Back-End |  |  |  | 2025-10-22 | 2026-01-28 | 5 |  |  | 3 | 2025-10-22 | 2026-01-28 | 5 | 99 | bar: 2
Note on M4: Daily / Weekly / Monthly: Use this to change the gantt chart view to Weekly or Monthly if you want to see a larger range of dates. Note that the weekly and monthly views result in a loss of detail.
Note on M5: Display Week / Display Month: Use this to change the starting week or month shown in the gantt chart.
Note on A7: WBS Level: Choose the WBS (Work Breakdown Structure) level from the drop-down in this column.
Note on B7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … The WBS uses a formula to automatically update the numbering.
Note on C7: Task Description Enter the name of each task and sub-task. The task description is automatically indented using conditional formatting based on the WBS Level column.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Predecessor Tasks: You may use this column to calculate the start date for the task based on the end date of the Predecessor you reference. Use a formula like =A13 to reference the WBS of the Predecessor task that must be completed before this task can start. You can also enter the WBS as a text value by entering an apostrophe before the number like '2.3. Avoid circular references, such as choosing the current task as its own Predecessor. Using this column assumes that you want the task to start on the next work day. See the Help worksheet for more examples of using formulas to create task dependencies.
Note on G7: Start Date You can manually enter the Start date for each task, use the Predecessor column to have a Start date calculated automatically, or use a formula to create a dependency on some other cell. See the Help worksheet for examples of creating dependencies.
Note on H7: End Date If you want to define the End date instead of calculating what it should be, enter the date in this column. Otherwise, enter a value in the Work Days or Calendar Days column to define the duration of the task.
Note on I7: Work Days Enter the number of Work Days that you estimate this task will require to complete. Work Days exclude the weekend (defined in the Help worksheet) and the holidays listed in the Holidays worksheet.
Note on J7: Duration: Calendar Days If you want to enter the number of calendar days instead of the number of work days, enter a value in this column.
Note on K7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on L7: Color (optional): The following letters can be used to change the color the incomplete portion of the bar. b = blue k = black x = gray o = orange y = yellow p = purple r = red g = green
Note on P7: Duration: Calendar Days The duration in calendar days is calculated as the End date minus the Start date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column. You can HIDE this column, but do not delete it.

## Holidays
Holidays to Exclude from Work Days
If you add more rows to the bottom of the list, you may need to
edit the named range "holidays" via Formulas > Named Ranges.
to include the new rows. The Description column is just for reference.
Date | Description | Country
2015-12-25 | Christmas
2016-12-25 | Christmas
2017-12-25 | Christmas
2018-12-25 | Christmas
2019-12-25 | Christmas
2020-12-25 | Christmas
2021-12-25 | Christmas
2022-12-25 | Christmas
2023-12-25 | Christmas
2024-12-25 | Christmas
2025-12-25 | Christmas
2015-01-01 | New Year's Day
2016-01-01 | New Year's Day
2017-01-01 | New Year's Day
2018-01-01 | New Year's Day
2019-01-01 | New Year's Day
2020-01-01 | New Year's Day
2021-01-01 | New Year's Day
2022-01-01 | New Year's Day
2023-01-01 | New Year's Day
2024-01-01 | New Year's Day
2025-01-01 | New Year's Day
2015-10-12 | Columbus Day | US
2016-10-10 | Columbus Day | US
2017-10-09 | Columbus Day | US
2018-10-08 | Columbus Day | US
2019-10-14 | Columbus Day | US
2020-10-12 | Columbus Day | US
2021-10-11 | Columbus Day | US
2022-10-10 | Columbus Day | US
2023-10-09 | Columbus Day | US
2024-10-14 | Columbus Day | US
2025-10-13 | Columbus Day | US
2015-07-04 | Independence Day | US
2016-07-04 | Independence Day | US
2017-07-04 | Independence Day | US
2018-07-04 | Independence Day | US
2019-07-04 | Independence Day | US
2020-07-04 | Independence Day | US
2021-07-04 | Independence Day | US
2022-07-04 | Independence Day | US
2023-07-04 | Independence Day | US
2024-07-04 | Independence Day | US
2025-07-04 | Independence Day | US
2015-09-07 | Labor Day | US
2016-09-05 | Labor Day | US
2017-09-04 | Labor Day | US
2018-09-03 | Labor Day | US
2019-09-02 | Labor Day | US
2020-09-07 | Labor Day | US
2021-09-06 | Labor Day | US
2022-09-05 | Labor Day | US
2023-09-04 | Labor Day | US
2024-09-02 | Labor Day | US
2025-09-01 | Labor Day | US
2015-01-19 | M.L.King Jr. Day | US
2016-01-18 | M.L.King Jr. Day | US
2017-01-16 | M.L.King Jr. Day | US
2018-01-15 | M.L.King Jr. Day | US
2019-01-21 | M.L.King Jr. Day | US
2020-01-20 | M.L.King Jr. Day | US
2021-01-18 | M.L.King Jr. Day | US
2022-01-17 | M.L.King Jr. Day | US
2023-01-16 | M.L.King Jr. Day | US
2024-01-15 | M.L.King Jr. Day | US
2025-01-20 | M.L.King Jr. Day | US
2015-05-25 | Memorial Day | US
2016-05-30 | Memorial Day | US
2017-05-29 | Memorial Day | US
2018-05-28 | Memorial Day | US
2019-05-27 | Memorial Day | US
2020-05-25 | Memorial Day | US
2021-05-31 | Memorial Day | US
2022-05-30 | Memorial Day | US
2023-05-29 | Memorial Day | US
2024-05-27 | Memorial Day | US
2025-05-26 | Memorial Day | US
2015-02-16 | Presidents Day | US
2016-02-15 | Presidents Day | US
2017-02-20 | Presidents Day | US
2018-02-19 | Presidents Day | US
2019-02-18 | Presidents Day | US
2020-02-17 | Presidents Day | US
2021-02-15 | Presidents Day | US
2022-02-21 | Presidents Day | US
2023-02-20 | Presidents Day | US
2024-02-19 | Presidents Day | US
2025-02-17 | Presidents Day | US
2015-11-26 | Thanksgiving | US
2016-11-24 | Thanksgiving | US
2017-11-23 | Thanksgiving | US
2018-11-22 | Thanksgiving | US
2019-11-28 | Thanksgiving | US
2020-11-26 | Thanksgiving | US
2021-11-25 | Thanksgiving | US
2022-11-24 | Thanksgiving | US
2023-11-23 | Thanksgiving | US
2024-11-28 | Thanksgiving | US
2025-11-27 | Thanksgiving | US
2015-11-11 | Veterans Day | US
2016-11-11 | Veterans Day | US
2017-11-11 | Veterans Day | US
2018-11-11 | Veterans Day | US
2019-11-11 | Veterans Day | US
2020-11-11 | Veterans Day | US
2021-11-11 | Veterans Day | US
2022-11-11 | Veterans Day | US
2023-11-11 | Veterans Day | US
2024-11-11 | Veterans Day | US
2025-11-11 | Veterans Day | US
2015-12-26 | Boxing Day | UK
2016-12-26 | Boxing Day | UK
2017-12-26 | Boxing Day | UK
2018-12-26 | Boxing Day | UK
2019-12-26 | Boxing Day | UK
2020-12-26 | Boxing Day | UK
2021-12-26 | Boxing Day | UK
2022-12-26 | Boxing Day | UK
2023-12-26 | Boxing Day | UK
2024-12-26 | Boxing Day | UK
2025-12-26 | Boxing Day | UK
2015-04-03 | Good Friday | UK
2016-03-25 | Good Friday | UK
2017-04-14 | Good Friday | UK
2018-03-30 | Good Friday | UK
2019-04-19 | Good Friday | UK
2020-04-10 | Good Friday | UK
2021-04-02 | Good Friday | UK
2022-04-15 | Good Friday | UK
2023-04-07 | Good Friday | UK
2024-03-29 | Good Friday | UK
2025-04-18 | Good Friday | UK
2015-04-06 | Easter Monday | UK
2016-03-28 | Easter Monday | UK
2017-04-17 | Easter Monday | UK
2018-04-02 | Easter Monday | UK
2019-04-22 | Easter Monday | UK
2020-04-13 | Easter Monday | UK
2021-04-05 | Easter Monday | UK
2022-04-18 | Easter Monday | UK
2023-04-10 | Easter Monday | UK
2024-04-01 | Easter Monday | UK
2025-04-21 | Easter Monday | UK
2015-05-04 | Early May Bank Holiday | UK
2016-05-02 | Early May Bank Holiday | UK
2017-05-01 | Early May Bank Holiday | UK
2018-05-07 | Early May Bank Holiday | UK
2019-05-06 | Early May Bank Holiday | UK
2020-05-04 | Early May Bank Holiday | UK
2021-05-03 | Early May Bank Holiday | UK
2022-05-02 | Early May Bank Holiday | UK
2023-05-01 | Early May Bank Holiday | UK
2024-05-06 | Early May Bank Holiday | UK
2025-05-05 | Early May Bank Holiday | UK
2015-05-25 | Spring Bank Holiday | UK
2016-05-30 | Spring Bank Holiday | UK
2017-05-29 | Spring Bank Holiday | UK
2018-05-28 | Spring Bank Holiday | UK
2019-05-27 | Spring Bank Holiday | UK
2020-05-25 | Spring Bank Holiday | UK
2021-05-31 | Spring Bank Holiday | UK
2022-05-30 | Spring Bank Holiday | UK
2023-05-29 | Spring Bank Holiday | UK
2024-05-27 | Spring Bank Holiday | UK
2025-05-26 | Spring Bank Holiday | UK
2015-08-03 | Summer Bank Holiday | UK
2016-08-01 | Summer Bank Holiday | UK
2017-08-07 | Summer Bank Holiday | UK
2018-08-06 | Summer Bank Holiday | UK
2019-08-05 | Summer Bank Holiday | UK
2020-08-03 | Summer Bank Holiday | UK
2021-08-02 | Summer Bank Holiday | UK
2022-08-01 | Summer Bank Holiday | UK
2023-08-07 | Summer Bank Holiday | UK
2024-08-05 | Summer Bank Holiday | UK
2025-08-04 | Summer Bank Holiday | UK
2015-08-31 | Late Summer Bank Holiday | UK
2016-08-29 | Late Summer Bank Holiday | UK
2017-08-28 | Late Summer Bank Holiday | UK
2018-08-27 | Late Summer Bank Holiday | UK
2019-08-26 | Late Summer Bank Holiday | UK
2020-08-31 | Late Summer Bank Holiday | UK
2021-08-30 | Late Summer Bank Holiday | UK
2022-08-29 | Late Summer Bank Holiday | UK
2023-08-28 | Late Summer Bank Holiday | UK
2024-08-26 | Late Summer Bank Holiday | UK
2025-08-25 | Late Summer Bank Holiday | UK

## Help
Help
Version: Gantt Chart Template 4.0 for Excel 2010 or Later, Excel Online, & Excel for iPad/iPhone
| If this page does not answer your questions, visit the following page: | Support
Intro
This Gantt Chart spreadsheet is designed to to help you create a simple project schedule. You
only need to know some basic spreadsheet operations, such as how to insert, delete, copy and
and paste rows and cells. For more advanced uses, such as defining task dependencies, you
will need to know how to enter formulas.
Be sure to read the Getting Started Tips below. It would also be a good idea to watch the demo videos on Vertex42.com. The demo videos use the desktop version of Excel, but much of the information is still applicable to users of Excel Online.
Watch the Demo Videos on Vertex42.com
Before sharing this spreadsheet, please read the license agreement in the TermsOfUse worksheet.
New in Version 4.0
- Choose the WBS Level from a drop-down to update the WBS numbering and automatically indent the Task Description.
- How you define the task start date and duration is greatly simplified and much more intuitive.
- The information in the header is positioned to allow you to hide columns that you do not need to see.
Features Unique to gantt-chart_o365.xlsx (compared to gantt-chart.xlsx)
This version of the Gantt Chart Template was designed to work in Online Excel and Excel for iPad and iPhone. It will also work in desktop versions of Excel 2010 or Later. Below are some of the notable additions or changes in this version.
• It uses the WORKDAY.INTL and NETWORKDAYS.INTL functions which allow you define which days of the week are considered non-working days (explained in the Help below).
• You can highlight the End date red when the task is overdue (explained in the Help below).
• Instead of changing the color of the bars to indicate completion status, conditional formatting is used to display a progress bar within the % Done column.
• The number of columns used to display the gantt chart had to be reduced, so the Weekly and Monthly views are less precise, meaning a week or month containing a 1-day task has a bar that is the same length as a week or month containing a 5-day task.
• You can define one Predecessor per task (instead of 3).
• The "Show Weekends" option was removed. In the Daily view, if you do not want to show weekends, you may hide the columns you do not want to show (though you would need to unhide them when using the Weekly or Monthly views).
Getting Started Tips
| • Edit the cells with the light green background. | Input Cell
| • Edit the [ Bracketed Text ] in the header (the project title and sub-title). | Input Cell
| • Edit cells within gray borders in the header and in the Holidays worksheet. | Input Cell
• Toggle between the Daily, Weekly, and Monthly view using the "Display:" drop-down box.
• To adjust the range of dates shown in the gantt chart, change the Display Week number.
| • Some of the labels include cell comments to provide extra help information. | Label
• The project Start date determines the first week shown in the gantt chart.
• To insert a new task, insert a new row, then with the new row selected, press Ctrl+d to copy
the formulas and formatting from the row immediately above the one you inserted.
• Edit the Holidays worksheet to define the dates that should be considered non-working days.
• If you see "#####" in a cell, widen the column to display the cell contents.
• Define the START of a task by entering a Predecessor or Start date.
• Define the END of a task by entering the End date, or Work Days, or Calendar Days.
• Backup your file regularly to avoid losing data! Excel files get corrupted occasionally.
Define the Weekend or NON-WORKING Days
weekend
| Choose an option or enter a weekend string → | 0000011
| The WORKDAYS.INTL() and NETWORKDAYS.INTL() functions allow you to specify | Option | Non-Work Days
| which day(s) of the week should be used as the weekend or non-working days. | 1 | Saturday, Sunday
|  | 2 | Sunday, Monday
| To use these functions, choose an option from the drop-down box on the right. | 3 | Monday, Tuesday
|  | 4 | Tuesday, Wednesday
| If one of the options to the right does not work for you, you can enter a string of | 5 | Wednesday, Thursday
| 7 characters, using a "1" to represent a non-workday and a "0" to represent | 6 | Thursday, Friday
| a work day, beginning with Monday. | 7 | Friday, Saturday
|  | 11 | Sunday Only
| For example, the string 0000011 would result in a Saturday-Sunday weekend. | 12 | Monday Only
|  | 13 | Tuesday Only
|  | 14 | Wednesday Only
|  | 15 | Thursday Only
|  | 16 | Friday Only
|  | 17 | Saturday Only
Change Dates to dd/mm/yyyy Format |  | Date Format
| If you would like to display dates in the gantt chart in UK format (dd/mm/yyyy) choose the | mdy
appropriate option to the right.
Add Rows (Insert New Tasks)
There are many ways to add more tasks. Most importantly, you need to remember to copy
formulas and formatting for the entire row when adding new rows. If you insert a row
between two tasks, the formatting is automatically copied, but you need to copy formulas.
Below are the recommended ways to add new rows.
Note: Use row operations by right-clicking on the Row #
Method 1: Insert a Row then Copy Formulas Down
1. Right-click on a row and select "Insert" (This inserts a row ABOVE the selected row)
2. Press Ctrl+d to copy formulas and formatting from the row above the new one.
3. Edit the green cells in your newly inserted row.
Method 2: Copy a Row down using the selection drag handle
Note: After inserting a row, you can select the row above it and use the selection drag
handle to copy the row down. This is also how you can easily add rows at the bottom.
The screenshot on the right shows the
selection drag handle for a selected row.
Method 3: Copy a Row and Insert the Copied Row
1. Right-click on a row and select "Copy"
2. Right-click on a row and select "Insert Copied Cells"
3. Edit the green cells in your newly inserted row.
Note: This method is not preferred because it can result in a messy set of conditional
formatting rules. Inserting rows and then copying down via Ctrl+d or using the drag handle
is the preferred method.
Delete a Row (Remove a Task)
Right-click on the row number of the row you want to delete and select Delete.
If this results in errors, then you probably had formulas that referenced cells in the deleted row.
Press CTRL+z to Undo, or search for #REF! errors and fix them.
Edit the WBS Numbering
Use the WBS Level column to choose the outline level for the WBS numbering.
A formula in the WBS column will automatically update the WBS number. The Task Description
is also indented using conditional formatting based on the WBS Level.
If you leave a blank cell above a WBS number, the numbering will reset to 1. The formulas are meant for convenience, but you can manually enter them if you need to. If you manually enter
WBS numbers, then you may need to enter them as text by preceding the number with an
apostrophe, such as '2. Just remember that if you enter them manually, the WBS Level
column cannot be used to change them.
Create Task Dependencies
You can use Excel formulas to make tasks adjust based on the start or end of another task.
Normally, a task dependency is used to define the start date to be the day after the end date
of a prior task. The prior task is called the "predecessor." Below are a few different ways that
you can create task dependencies using Excel formulas.
Method 1: Creating Your Own Formulas
Entering your own formulas allows you to do whatever you want, but may be more difficult. Also, it may not be easy for somebody else to identify your task dependencies.
A. Reference the project Start date (e.g. =$C$4 )
B. Set the Start date to the next Work Day after another task's End date.
- Use the formula =WORKDAY.INTL(enddate,1,weekend,holidays) where enddate is the reference to the End date of a predecessor task.
- For multiple predecessors, the formula would be
=WORKDAY.INTL(MAX(enddate1,enddate2,enddate3),1,weekend,holidays)
C. Set the Start date to the next Calendar Day after another task's End date.
- This formula is very simple: =enddate+1
- For multiple predecessors, the formula would be =MAX(enddate1,enddate2,enddate3)+1
D. Set the Start date to a number of Work days before or after another date.
- This formula is just like the one in C or D, except that in place of the "1" you enter the number of days, such as =WORKDAY.INTL(startdate,-5,weekend,holidays)
Note: Refer to Excel's Help system to learn more about the WORKDAY() and WORKDAY.INTL() functions.
Method 2: Using the Predecessor Column
The Predecessor column makes it easy to create a task dependency where the Start date is the next Work Day after a predecessor's end date. To use the Predecessor column, you must enter the WBS for the predecessor task using a formula or as text.
A. Reference a Predecessor using a formula.
In the predecessor column, press "=" and then click on the cell containing the WBS that you want to reference. Then press Enter. This is the preferred method.
B. Enter the Predecessor manually as text.
You can enter the Predecessor manually, but you must make sure that you enter it as text, or you will end up with a bunch of #NA errors. To enter 1.3 as text, just add an apostrophe at the beginning like this: '1.3.
Note: This is not the best method, because if you insert a new task, you'll have to update all of the Predecessors again, or at least verify that they are still correct.
Change the End Date Font to Red when Behind Schedule
|  | Feature on/off: | off
Conditional formatting can be used to do some very useful things. One feature built into this spreadsheet is the option to change the font color of the End date to red when it is approaching the current date and also make it bold when the task is past due.
| Change the urgency days to the right to determine when the End date will change to red. | Urgency days: | 7
Start the Week on Sunday instead of Monday
The option to the right will allow you to choose to display the work week starting with Sunday instead of Monday. This affects the chart display only, not any other work day formulas.
|  | Start Day: | Monday | 2
Change the Color of the Bars in the Gantt Chart
Color Column:
The cells that make up the chart area use conditional formatting to control the color of the bars. The default color is blue. You can make the bars different colors by entering one of the following letters in the color column:
Colors: b=blue, k=black, g=green, p=purple, o=orange, r=red, x=gray, y=yellow
You can also enter a number 1-6 to use an accent color from the theme palette.
Advanced Uses of the Color Column
Use a Formula to Change the Color Based on Percent Complete
Using a reference to the %Done column, you can change the color of the bar to gray using the following formula in the color column. Note that "x" and "b" are the colors for gray and blue.
=IF(percent_done>=100%,"x","b")
| Use a Formula to Show Urgency |  | Urgency (Days)
| You can enter a formula in the Color column to change the color to orange based on a | red | 2
| comparison of the End date and Today's date. For example, the following formula would give | orange | 14
| you a 10-day warning, where end_date is a reference to the End date cell. | yellow | 28
=IF(end_date<TODAY()+10,"o","")
The example below makes the 10-day warning orange and a 2-day warning red.
=IF(end_date<TODAY()+2,"r",IF(end_date<TODAY()+10,"o",""))
The fancy formula below makes use of the table of urgency values to the right. Note that "urgency_days" is a named range referring to the table on the right.
=IF(end_date<TODAY()+INDEX(urgency_days,1),"r", IF(end_date<TODAY()+ INDEX(urgency_days,2),"o",IF(end_date<TODAY()+ INDEX(urgency_days,3),"y","")))
| Color-Code Based on Lead Name | Names | Color
| One popular reason for color-coding is to help identify ownership of a task. To do this, | Bob | k
| you could create your own nested IF formula: =IF(ref="Bob","o",If(ref="Sally","p","")) | Sarah | x
| where "ref" is the reference to the cell in the Lead column. | Bill | b
|  | Jim | g
| If you want to use the table listed to the right of this help section, you can edit the following |  | p
| formula in the Color column. Note that the Names must match exactly. |  | y
| =IFERROR( INDEX( lead_color, MATCH( ref, lead_names, 0) ), "") |  | o
r
FAQs
Q: | How do I make a Summary task show the MIN(start) and MAX(end) for a group of sub-tasks?
This can be done by entering =MIN(startdates) for the Start date and =MAX(enddates) for the End date, where startdates and enddates are references to the range of start dates and end dates for the group of sub tasks.
Q: | How do I calculate the %Complete for an entire category of tasks?
The %Complete for a category task can be calculated from its sub tasks using the formula below, where "workdays" is a reference to the range of work day values and "complete" is a reference to the %complete for each of the subtasks.
=SUMPRODUCT(workdays,complete)/SUM(workdays)
Example: =SUMPRODUCT(H9:H15,J9:J15)/SUM(H9:H15)
Let's say you have 3 sub tasks that are 10 days, 12 days, and 14 days long, respectively. If the first subtask is 50% complete and the others are 25% complete, you could calculate the overall percent complete for the group as: =(10*50%+12*25%+14*25%)/(10+12+14).
Q: | How do I change the Print Settings? (Excel 2010, 2013)
Select the entire range of cells you want to print and go to File > Print Area > Set Print Area.
Then go to File > Page Setup or File > Print Preview and adjust the Scaling, Margins, and
Page Orientation as desired.
Q: | Can I use CUT/PASTE to move tasks around?
Yes, the formulas in this spreadsheet were designed to allow you to move tasks around by cutting and inserting the cut rows. Remember, you must move entire rows. Behind the scenes, this may result in a lot of duplicate conditional formatting rules. So, it is best to start a new project with a new spreadsheet rather than one that you have edited heavily.
Q: | Can I use Autofilter?
Yes, if you must. However, avoid using Sort unless you know exactly what you are doing and how sorting will make all the WBS numbering change.
Q: | I've messed up the chart area somehow. How do I fix it?
Find a row that works, then copy the cells that make up the gantt chart area from that row into the row that is messed up.
© 2006-2016 Vertex42 LLC
Note on C37: This is an example comment.

## TermsOfUse
Terms of Use
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
By Vertex42.com
© 2006-2016 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
See License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet. If necessary, you may hide it by right-clicking on the tab and selecting Hide.